## Summary
Metric | Value
Report | Agentic QE Platform - MVP - Cycle report
Cycle | Commission baseline (CYC-4, baseline)
Status | completed
Baseline | BL-4 v1
SUT build | demo/commission-engine
Requirements | 14
Delta | n/a (baseline)
Test cases | 15
Test cases by type | {"functional":14,"non-functional":1}
Test cases by label | {"functional":14,"automation":14,"non-functional":1}
Scripts | 13
Executed (real) | 14
Passed | 13
Failed | 1
Pass rate % | 92.9
Execution tool | Playwright 1.63.0 (headless Chromium, JSON reporter)
Defects | 1
Coverage (passing %) | 85.7
Narrative | Commission baseline (baseline) worked from Jira initiative COM-1 (pulled live from GitHub), Jira epic COM-10 (pulled live from GitHub), Codebase sri465inno/uc-agentic-quality-engineering@demo/commission-engine (df5203e) (pulled live from GitHub). The reviewed requirement set holds 14 requirements. 15 test cases are designed, 14 of them automated in 13 Playwright scripts. Execution ran 14 automated cases for real: 13 passed and 1 failed (pass rate 92.9%). 1 defect(s) were raised from real failures: DEF-001 A stay of exactly 7 nights earns the 1.5% long-stay bonus: returns 80 instead of 92.
Narrative drafted by | Deterministic template (demo mode - no model API key set)

## Inputs
Input | Reference | Statements | Provenance | Provenance detail
Jira initiative | COM-1 | 3 | github | Jira REST API v3 export pulled live from GitHub (sri465inno/uc-agentic-quality-engineering@demo/jira-export) - synthetic test issues; no live Jira call was made
Jira epic | COM-10 | 8 | github | Jira REST API v3 export pulled live from GitHub (sri465inno/uc-agentic-quality-engineering@demo/jira-export) - synthetic test issues; no live Jira call was made
Codebase | sri465inno/uc-agentic-quality-engineering@demo/commission-engine (df5203e) | 16 | github | Pulled live from GitHub: git clone of sri465inno/uc-agentic-quality-engineering@demo/commission-engine (df5203e) at 2026-10-02T03:54:15.412Z

## Requirements
ID | Requirement | Type | Status | Version | Superseded value
REQ-001 | Every reservation is described by a data dictionary of 1000 attributes. | functional | new | 1
REQ-002 | Travel advisors can view the commission breakdown for a reservation online. | functional | new | 1
REQ-003 | Commission quotes return within 300 ms at the 95th percentile. | non-functional | new | 1
REQ-004 | Base commission is 10% of commissionable room revenue. | functional | new | 1
REQ-005 | Commissionable room revenue excludes taxes, resort fees and ancillary charges. | functional | new | 1
REQ-006 | Reservations booked through the GDS channel earn an additional 1.5% channel uplift. | functional | new | 1
REQ-007 | Stays of 7 nights or more earn a long-stay bonus of 1.5%. | functional | new | 1
REQ-008 | Commission per reservation is capped at USD 500. | functional | new | 1
REQ-009 | Commission is rounded half-up to 2 decimal places. | functional | new | 1
REQ-010 | Reservations paid with loyalty points are not commissionable. | functional | new | 1
REQ-011 | Cancelled and no-show reservations earn no commission. | functional | new | 1
REQ-012 | Every commission calculation is written to the commission audit ledger. | functional | new | 1
REQ-013 | A reservation without an advisor IATA number returns HTTP 422. | functional | new | 1
REQ-014 | Unknown reservation IDs return HTTP 404. | functional | new | 1

## Test Cases
Key | Name | Objective | Precondition | Test Step | Test Data | Expected Result | Priority | Type | Labels | Requirement link | Automation status | Cycle | Change | Revision note
TC-F-001 | The reservation model has 1000 attributes and a full reservation is accepted | Verify the data dictionary defines 1000 attributes and a quote carrying all of them is accepted. | The commission engine is running. | 1. GET /api/data-dictionary and count the attributes 2. Quote a reservation carrying every attribute 3. Read attributesReceived | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | 1000 attributes; quote HTTP 200 with attributesReceived = 1000 | Medium | Functional | functional, automation | COM-1, REQ-001, BR-001 | Automated | Commission baseline | Baseline
TC-F-002 | Advisor views the commission breakdown on the commission statement page | Verify a travel advisor can look up a reservation and see its commission breakdown in the browser. | A stored GDS reservation; the commission statement page is reachable. | 1. Store a full reservation (POST /api/reservations) 2. Open the commission statement page 3. Enter the reservation ID and click "Show commission" 4. Read the breakdown | reservation.status=CONFIRMED; channel.bookingChannel=GDS; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | Page shows "Commission breakdown", the base commission line and "Total commission" | Medium | Functional | functional, automation | COM-1, REQ-002, BR-002 | Automated | Commission baseline | Baseline
TC-N-001 | Commission quote p95 response time is within 300 ms | Verify the 95th percentile of 20 full-reservation commission quotes is at most 300 ms. | The commission engine is running. | 1. Build a full 1000-attribute reservation 2. POST /api/commission/quote 20 times, timing each call 3. Compute the p95 latency | samples=20; reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | p95 <= 300 ms | Medium | Non-functional | non-functional, automation | COM-1, REQ-003, BR-003 | Automated | Commission baseline | Baseline
TC-F-003 | Base commission is 10% of commissionable room revenue | Verify a standard direct reservation earns 10% of its commissionable room revenue. | Direct booking, 3 nights, BAR rate, 1 room, paid by card. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: standard direct reservation 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, effective rate 10% and commission USD 80.00 (10% of USD 800.00) | High | Functional | functional, automation | COM-10, REQ-004, BR-004 | Automated | Commission baseline | Baseline
TC-F-004 | Taxes, resort fees and ancillaries are excluded from commissionable revenue | Verify commissionable room revenue = total - taxes - resort fees - ancillary charges. | A reservation whose total includes tax, resort fee and ancillary charges. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: revenue.totalAmount 1000.00 with tax 120.00, resort fee 30.00, ancillaries 50.00 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200 and commissionableRevenue = USD 800.00 | High | Functional | functional, automation | COM-10, REQ-005, BR-005 | Automated | Commission baseline | Baseline
TC-F-005 | GDS reservations earn an additional 1.5% channel uplift | Verify a GDS booking is commissioned at 10% base + 1.5% uplift = 11.5%. | GDS booking, 3 nights, BAR rate, 1 room. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: channel.bookingChannel=GDS 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=GDS; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, effective rate 11.5% and commission USD 92.00 | High | Functional | functional, automation | COM-10, REQ-006, BR-006 | Automated | Commission baseline | Baseline
TC-F-006 | A stay of exactly 7 nights earns the 1.5% long-stay bonus | Verify the long-stay bonus applies at the 7-night boundary ("7 nights or more"). | Direct booking of exactly 7 nights. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: stay.nights=7 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=7; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, effective rate 11.5% and commission USD 92.00 | High | Functional | functional, automation | COM-10, REQ-007, BR-007 | Automated | Commission baseline | Baseline
TC-F-007 | A stay of 6 nights earns no long-stay bonus | Verify the long-stay bonus does not apply below 7 nights. | Direct booking of 6 nights. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: stay.nights=6 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=6; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, effective rate 10% and commission USD 80.00 | High | Functional | functional, automation | COM-10, REQ-007, BR-007 | Automated | Commission baseline | Baseline
TC-F-008 | Commission is capped at USD 500 per reservation | Verify a reservation whose uncapped commission exceeds USD 500 pays exactly USD 500. | High-value direct booking: uncapped commission USD 800.00. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: revenue.totalAmount=8000 (no tax, fees or ancillaries) 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=8000; revenue.taxAmount=0; revenue.resortFeeAmount=0; revenue.ancillaryAmount=0; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, capped = true and commission USD 500.00 | High | Functional | functional, automation | COM-10, REQ-008, BR-008 | Automated | Commission baseline | Baseline
TC-F-009 | Commission is rounded half-up to 2 decimal places | Verify 10% of USD 123.45 (12.345) is rounded half-up, not truncated. | Direct booking whose raw commission has a third decimal of 5. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: revenue.totalAmount=123.45 (no tax, fees or ancillaries) 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=123.45; revenue.taxAmount=0; revenue.resortFeeAmount=0; revenue.ancillaryAmount=0; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200 and commission USD 12.35 | High | Functional | functional, automation | COM-10, REQ-009, BR-009 | Automated | Commission baseline | Baseline
TC-F-010 | A stay paid with loyalty points earns no commission | Verify reservations redeemed with loyalty points are not commissionable. | Direct booking paid with loyalty points. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: payment.loyaltyPointsRedemption=true 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=true; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, eligible = false and commission USD 0.00 | High | Functional | functional, automation | COM-11, REQ-010, BR-010 | Automated | Commission baseline | Baseline
TC-F-011 | Cancelled and no-show reservations earn no commission | Verify reservation.status CANCELLED and NO_SHOW both return a commission of 0. | Two otherwise standard reservations with status CANCELLED and NO_SHOW. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: reservation.status=CANCELLED, then reservation.status=NO_SHOW 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CANCELLED ¦ NO_SHOW; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | Both quotes: HTTP 200, eligible = false and commission USD 0.00 | High | Functional | functional, automation | COM-11, REQ-011, BR-011 | Automated | Commission baseline | Baseline
TC-F-012 | Verify: Every commission calculation is written to the commission audit ledger | Confirm the behaviour "Every commission calculation is written to the commission audit ledger." (no executable template in the catalogue - manual verification). | Access to the system under test and its operational logs. | 1. Perform the action described by the requirement 2. Observe the outcome in the system or its logs | n/a | Every commission calculation is written to the commission audit ledger. | Low | Functional | functional | README.md, REQ-012, BR-012 | Not automated | Commission baseline | Baseline
TC-F-013 | A reservation without an advisor IATA number returns HTTP 422 | Verify the quote is rejected with HTTP 422 when advisor.iataNumber is empty. | A reservation with no booking advisor. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: advisor.iataNumber empty 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; advisor.iataNumber=; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 422 | Medium | Functional | functional, automation | README.md, REQ-013, BR-013 | Automated | Commission baseline | Baseline
TC-F-014 | Commission for an unknown reservation ID returns HTTP 404 | Verify looking up the commission of a non-existent reservation returns HTTP 404. | Reservation RES-UNKNOWN-0000 does not exist. | 1. GET /api/reservations/RES-UNKNOWN-0000/commission | id=RES-UNKNOWN-0000 | HTTP 404 | Medium | Functional | functional, automation | README.md, REQ-014, BR-014 | Automated | Commission baseline | Baseline

## Execution
Case | Requirement | Name | Result | Duration ms | Note
TC-F-001 | REQ-001 | The reservation model has 1000 attributes and a full reservation is accepted | passed | 37
TC-F-002 | REQ-002 | Advisor views the commission breakdown on the commission statement page | passed | 226
TC-N-001 | REQ-003 | Commission quote p95 response time is within 300 ms | passed | 51
TC-F-003 | REQ-004 | Base commission is 10% of commissionable room revenue | passed | 8
TC-F-004 | REQ-005 | Taxes, resort fees and ancillaries are excluded from commissionable revenue | passed | 6
TC-F-005 | REQ-006 | GDS reservations earn an additional 1.5% channel uplift | passed | 9
TC-F-006 | REQ-007 | A stay of exactly 7 nights earns the 1.5% long-stay bonus | failed | 6
TC-F-007 | REQ-007 | A stay of 6 nights earns no long-stay bonus | passed | 22
TC-F-008 | REQ-008 | Commission is capped at USD 500 per reservation | passed | 8
TC-F-009 | REQ-009 | Commission is rounded half-up to 2 decimal places | passed | 12
TC-F-010 | REQ-010 | A stay paid with loyalty points earns no commission | passed | 7
TC-F-011 | REQ-011 | Cancelled and no-show reservations earn no commission | passed | 10
TC-F-012 | REQ-012 | Verify: Every commission calculation is written to the commission audit ledger | not-run | 0 | Manual test case - not automated, not executed
TC-F-013 | REQ-013 | A reservation without an advisor IATA number returns HTTP 422 | passed | 7
TC-F-014 | REQ-014 | Commission for an unknown reservation ID returns HTTP 404 | passed | 4

## Defects
ID | Title | Severity | Case | Requirement | Expected | Actual | Failing assertion | Movement
DEF-001 | A stay of exactly 7 nights earns the 1.5% long-stay bonus: returns 80 instead of 92 | Critical | TC-F-006 | REQ-007 | 92 | 80 | expect(r.body.commission).toBe(92); | new

## Coverage
Requirement | Text | Cases | Automated | Executed | Failed | Status
REQ-001 | Every reservation is described by a data dictionary of 1000 attributes. | 1 | 1 | 1 | 0 | executed - passing
REQ-002 | Travel advisors can view the commission breakdown for a reservation online. | 1 | 1 | 1 | 0 | executed - passing
REQ-003 | Commission quotes return within 300 ms at the 95th percentile. | 1 | 1 | 1 | 0 | executed - passing
REQ-004 | Base commission is 10% of commissionable room revenue. | 1 | 1 | 1 | 0 | executed - passing
REQ-005 | Commissionable room revenue excludes taxes, resort fees and ancillary charges. | 1 | 1 | 1 | 0 | executed - passing
REQ-006 | Reservations booked through the GDS channel earn an additional 1.5% channel uplift. | 1 | 1 | 1 | 0 | executed - passing
REQ-007 | Stays of 7 nights or more earn a long-stay bonus of 1.5%. | 2 | 2 | 2 | 1 | executed - failing
REQ-008 | Commission per reservation is capped at USD 500. | 1 | 1 | 1 | 0 | executed - passing
REQ-009 | Commission is rounded half-up to 2 decimal places. | 1 | 1 | 1 | 0 | executed - passing
REQ-010 | Reservations paid with loyalty points are not commissionable. | 1 | 1 | 1 | 0 | executed - passing
REQ-011 | Cancelled and no-show reservations earn no commission. | 1 | 1 | 1 | 0 | executed - passing
REQ-012 | Every commission calculation is written to the commission audit ledger. | 1 | 0 | 0 | 0 | designed only (manual)
REQ-013 | A reservation without an advisor IATA number returns HTTP 422. | 1 | 1 | 1 | 0 | executed - passing
REQ-014 | Unknown reservation IDs return HTTP 404. | 1 | 1 | 1 | 0 | executed - passing

## Attribute coverage
Attribute | Description | Varied by cases | Status
reservation.status | Lifecycle status of the reservation | TC-F-011 | exercised - passing
stay.nights | Number of room nights | TC-F-006, TC-F-007 | exercised - failing
room.roomCount | Number of rooms held under the reservation |  | not exercised
rate.planCategory | Category of the booked rate plan |  | not exercised
revenue.totalAmount | Gross amount charged, including taxes, fees and ancillaries | TC-F-008, TC-F-009 | exercised - passing
revenue.taxAmount | Taxes included in revenue.totalAmount | TC-F-004 | exercised - passing
revenue.resortFeeAmount | Resort fees included in revenue.totalAmount | TC-F-004 | exercised - passing
revenue.ancillaryAmount | Ancillary charges (spa, dining, parking) included in revenue.totalAmount | TC-F-004 | exercised - passing
channel.bookingChannel | Channel the reservation was booked through | TC-F-005 | exercised - passing
advisor.iataNumber | IATA number of the booking travel advisor | TC-F-013 | exercised - passing
payment.loyaltyPointsRedemption | True when the stay is paid with loyalty points | TC-F-010 | exercised - passing

## Approvals
Gate | Decision | By | When | Detail
Requirement set review | approved | Priya Shah | 2026-10-02T03:54:16.127Z | 14 requirements approved; 0 excluded; 1 conflict(s) resolved

## Skills
Skill id | Name | Description | Seen by agents | File
automation-script-conventions | Automation script conventions | How every generated Playwright spec is shaped, named and asserted, so scripts stay reviewable and runnable cycle after cycle. | scripts | automation-script-conventions.md
cycle-report | Test cycle report | The fixed shape of every cycle report, so two cycles can be read side by side without translation. | report | cycle-report.md
defect-reporting | Defect reporting | What a defect must contain before it is raised, so every cycle's defects read the same and are actionable. | defects | defect-reporting.md
incremental-merge | Incremental load and merge rules | How an addition is classified against the baseline and what a human must see before it merges. | delta, rules, testcases, scripts | incremental-merge.md
input-normalisation | Input normalisation and provenance | How several inputs become one requirement set, and what must be visible about where each statement came from. | normalise, rules | input-normalisation.md
input-review | Input review before the human gate | What the review agent checks in the project inputs and how it words its suggestions for the reviewer. | review-agent | input-review.md
test-case-authoring | Test case authoring and Zephyr export shape | One house style for every test case, so each cycle exports into Zephyr the same way. | testcases, report | test-case-authoring.md
test-data-generation | Test data generation from the input specs | Every test case gets a complete, spec-conformant data set built from the data dictionary in the codebase input. | testdata | test-data-generation.md
testing-regression | Regression pack | Steers the design and execution agents to keep and re-run the full pack so nothing that worked before breaks. | testcases, scripts, execution | testing-regression.md
traceability-handover | Traceability hand-over | What each phase owes the next one so the chain from input to defect never breaks in any cycle. | normalise, requirements, rules, testcases, testdata, scripts, execution, defects, report | traceability-handover.md

## Hand-overs
Phase | Skills seen | Hand-over | Missing | Artefacts owed
Normalise (3-way compare) | input-normalisation, traceability-handover | complete |  | statements: delivered; gaps: delivered; conflicts: delivered
| input-review | complete |  | suggestions: delivered
Requirements repository agent | traceability-handover | complete |  | requirements: delivered
Business rules agent | incremental-merge, input-normalisation, traceability-handover | complete |  | businessRules: delivered
Test case agent | incremental-merge, test-case-authoring, testing-regression, traceability-handover | complete |  | functional: delivered; nonFunctional: delivered; regressionPack: delivered
Test data agent | test-data-generation, traceability-handover | complete |  | dataSets: delivered; specConformance: delivered
Automation script agent | automation-script-conventions, incremental-merge, testing-regression, traceability-handover | complete |  | specs: delivered
Execution agent (Playwright, real run) | testing-regression, traceability-handover | complete |  | results: delivered
Defect agent | defect-reporting, traceability-handover | complete |  | defects: delivered
Cycle report agent | cycle-report, test-case-authoring, traceability-handover | complete |  | cycleReport: delivered; comparison: n/a; testCaseExport: delivered