## Summary
Metric | Value
Report | Agentic QE Platform - MVP - Cycle report
Cycle | Commission increment (COM-20, engine 2.0) (CYC-5, incremental)
Status | completed
Baseline | BL-4 v2
SUT build | demo/commission-engine-v2
Requirements | 17
Delta | 10 unchanged · 1 enhanced · 3 new
Test cases | 19
Test cases by type | {"functional":18,"non-functional":1}
Test cases by label | {"functional":18,"automation":18,"regression":14,"non-functional":1}
Scripts | 16
Executed (real) | 18
Passed | 17
Failed | 1
Pass rate % | 94.4
Execution tool | Playwright 1.63.0 (headless Chromium, JSON reporter)
Defects | 1
Coverage (passing %) | 88.2
Narrative | Commission increment (COM-20, engine 2.0) (incremental) worked from Jira epic COM-20 (pulled live from GitHub), Codebase sri465inno/uc-agentic-quality-engineering@demo/commission-engine-v2 (6ccd807) (pulled live from GitHub). The reviewed requirement set holds 17 requirements (10 unchanged · 1 enhanced · 3 new). 19 test cases are designed, 18 of them automated in 16 Playwright scripts. Execution ran 18 automated cases for real: 17 passed and 1 failed (pass rate 94.4%). 1 defect(s) were raised from real failures: DEF-001 A stay of exactly 7 nights earns the 1.5% long-stay bonus: returns 80 instead of 92.
Narrative drafted by | Deterministic template (demo mode - no model API key set)

## Inputs
Input | Reference | Statements | Provenance | Provenance detail
Jira epic | COM-20 | 3 | github | Jira REST API v3 export pulled live from GitHub (sri465inno/uc-agentic-quality-engineering@demo/jira-export) - synthetic test issues; no live Jira call was made
Codebase | sri465inno/uc-agentic-quality-engineering@demo/commission-engine-v2 (6ccd807) | 20 | github | Pulled live from GitHub: git clone of sri465inno/uc-agentic-quality-engineering@demo/commission-engine-v2 (6ccd807) at 2026-10-02T04:13:56.665Z

## Requirements
ID | Requirement | Type | Status | Version | Superseded value
REQ-001 | Every reservation is described by a data dictionary of 1000 attributes. | functional | unchanged | 1
REQ-002 | Travel advisors can view the commission breakdown for a reservation online. | functional | carried over | 1
REQ-003 | Commission quotes return within 300 ms at the 95th percentile. | non-functional | carried over | 1
REQ-004 | Base commission is 10% of commissionable room revenue. | functional | unchanged | 1
REQ-005 | Commissionable room revenue excludes taxes, resort fees and ancillary charges. | functional | unchanged | 1
REQ-006 | Reservations booked through the GDS channel earn an additional 1.5% channel uplift. | functional | unchanged | 1
REQ-007 | Stays of 7 nights or more earn a long-stay bonus of 1.5%. | functional | unchanged | 1
REQ-008 | Commission per reservation is capped at USD 750. | functional | enhanced | 2 | Commission per reservation is capped at USD 500.
REQ-009 | Commission is rounded half-up to 2 decimal places. | functional | unchanged | 1
REQ-010 | Reservations paid with loyalty points are not commissionable. | functional | unchanged | 1
REQ-011 | Cancelled and no-show reservations earn no commission. | functional | carried over | 1
REQ-012 | Every commission calculation is written to the commission audit ledger. | functional | unchanged | 1
REQ-013 | A reservation without an advisor IATA number returns HTTP 422. | functional | unchanged | 1
REQ-014 | Unknown reservation IDs return HTTP 404. | functional | unchanged | 1
REQ-015 | Group reservations of 10 or more rooms are commissioned at a flat 8%. | functional | new | 1
REQ-016 | Package rates are commissioned on 70% of the package price. | functional | new | 1
REQ-017 | Negotiated corporate rates (rate plan CORP) are commissioned at a flat 5%. | functional | new | 1

## Test Cases
Key | Name | Objective | Precondition | Test Step | Test Data | Expected Result | Priority | Type | Labels | Requirement link | Automation status | Cycle | Change | Revision note
TC-F-001 | The reservation model has 1000 attributes and a full reservation is accepted | Verify the data dictionary defines 1000 attributes and a quote carrying all of them is accepted. | The commission engine is running. | 1. GET /api/data-dictionary and count the attributes 2. Quote a reservation carrying every attribute 3. Read attributesReceived | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | 1000 attributes; quote HTTP 200 with attributesReceived = 1000 | Medium | Functional | functional, automation, regression | COM-1, REQ-001, BR-001 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-002 | Advisor views the commission breakdown on the commission statement page | Verify a travel advisor can look up a reservation and see its commission breakdown in the browser. | A stored GDS reservation; the commission statement page is reachable. | 1. Store a full reservation (POST /api/reservations) 2. Open the commission statement page 3. Enter the reservation ID and click "Show commission" 4. Read the breakdown | reservation.status=CONFIRMED; channel.bookingChannel=GDS; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | Page shows "Commission breakdown", the base commission line and "Total commission" | Medium | Functional | functional, automation, regression | COM-1, REQ-002, BR-002 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-N-001 | Commission quote p95 response time is within 300 ms | Verify the 95th percentile of 20 full-reservation commission quotes is at most 300 ms. | The commission engine is running. | 1. Build a full 1000-attribute reservation 2. POST /api/commission/quote 20 times, timing each call 3. Compute the p95 latency | samples=20; reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | p95 <= 300 ms | Medium | Non-functional | non-functional, automation, regression | COM-1, REQ-003, BR-003 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-003 | Base commission is 10% of commissionable room revenue | Verify a standard direct reservation earns 10% of its commissionable room revenue. | Direct booking, 3 nights, BAR rate, 1 room, paid by card. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: standard direct reservation 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, effective rate 10% and commission USD 80.00 (10% of USD 800.00) | High | Functional | functional, automation, regression | COM-10, REQ-004, BR-004 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-004 | Taxes, resort fees and ancillaries are excluded from commissionable revenue | Verify commissionable room revenue = total - taxes - resort fees - ancillary charges. | A reservation whose total includes tax, resort fee and ancillary charges. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: revenue.totalAmount 1000.00 with tax 120.00, resort fee 30.00, ancillaries 50.00 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200 and commissionableRevenue = USD 800.00 | High | Functional | functional, automation, regression | COM-10, REQ-005, BR-005 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-005 | GDS reservations earn an additional 1.5% channel uplift | Verify a GDS booking is commissioned at 10% base + 1.5% uplift = 11.5%. | GDS booking, 3 nights, BAR rate, 1 room. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: channel.bookingChannel=GDS 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=GDS; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, effective rate 11.5% and commission USD 92.00 | High | Functional | functional, automation, regression | COM-10, REQ-006, BR-006 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-006 | A stay of exactly 7 nights earns the 1.5% long-stay bonus | Verify the long-stay bonus applies at the 7-night boundary ("7 nights or more"). | Direct booking of exactly 7 nights. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: stay.nights=7 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=7; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, effective rate 11.5% and commission USD 92.00 | High | Functional | functional, automation, regression | COM-10, REQ-007, BR-007 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-007 | A stay of 6 nights earns no long-stay bonus | Verify the long-stay bonus does not apply below 7 nights. | Direct booking of 6 nights. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: stay.nights=6 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=6; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, effective rate 10% and commission USD 80.00 | High | Functional | functional, automation, regression | COM-10, REQ-007, BR-007 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-008 | Commission is capped at USD 750 per reservation | Verify a reservation whose uncapped commission exceeds USD 750 pays exactly USD 750. | High-value direct booking: uncapped commission USD 1200.00. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: revenue.totalAmount=12000 (no tax, fees or ancillaries) 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=12000; revenue.taxAmount=0; revenue.resortFeeAmount=0; revenue.ancillaryAmount=0; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, capped = true and commission USD 750.00 | High | Functional | functional, automation | COM-10, COM-20, REQ-008, BR-008 | Automated | Commission increment (COM-20, engine 2.0) | Changed | v2 (CYC-5): name was "Commission is capped at USD 500 per reservation"; expected was "HTTP 200, capped = true and commission USD 500.00"; testData was "reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=8000; revenue.taxAmount=0; revenue.resortFeeAmount=0; revenue.ancillaryAmount=0; every other attribute of the 1000-attribute reservation from the data dictionary examples"
TC-F-009 | Commission is rounded half-up to 2 decimal places | Verify 10% of USD 123.45 (12.345) is rounded half-up, not truncated. | Direct booking whose raw commission has a third decimal of 5. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: revenue.totalAmount=123.45 (no tax, fees or ancillaries) 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=123.45; revenue.taxAmount=0; revenue.resortFeeAmount=0; revenue.ancillaryAmount=0; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200 and commission USD 12.35 | High | Functional | functional, automation, regression | COM-10, REQ-009, BR-009 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-010 | A stay paid with loyalty points earns no commission | Verify reservations redeemed with loyalty points are not commissionable. | Direct booking paid with loyalty points. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: payment.loyaltyPointsRedemption=true 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=true; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, eligible = false and commission USD 0.00 | High | Functional | functional, automation, regression | COM-11, REQ-010, BR-010 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-011 | Cancelled and no-show reservations earn no commission | Verify reservation.status CANCELLED and NO_SHOW both return a commission of 0. | Two otherwise standard reservations with status CANCELLED and NO_SHOW. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: reservation.status=CANCELLED, then reservation.status=NO_SHOW 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CANCELLED ¦ NO_SHOW; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | Both quotes: HTTP 200, eligible = false and commission USD 0.00 | High | Functional | functional, automation, regression | COM-11, REQ-011, BR-011 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-012 | Verify: Every commission calculation is written to the commission audit ledger | Confirm the behaviour "Every commission calculation is written to the commission audit ledger." (no executable template in the catalogue - manual verification). | Access to the system under test and its operational logs. | 1. Perform the action described by the requirement 2. Observe the outcome in the system or its logs | n/a | Every commission calculation is written to the commission audit ledger. | Low | Functional | functional, regression | README.md, REQ-012, BR-012 | Not automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-013 | A reservation without an advisor IATA number returns HTTP 422 | Verify the quote is rejected with HTTP 422 when advisor.iataNumber is empty. | A reservation with no booking advisor. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: advisor.iataNumber empty 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; advisor.iataNumber=; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 422 | Medium | Functional | functional, automation, regression | README.md, REQ-013, BR-013 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-014 | Commission for an unknown reservation ID returns HTTP 404 | Verify looking up the commission of a non-existent reservation returns HTTP 404. | Reservation RES-UNKNOWN-0000 does not exist. | 1. GET /api/reservations/RES-UNKNOWN-0000/commission | id=RES-UNKNOWN-0000 | HTTP 404 | Medium | Functional | functional, automation, regression | README.md, REQ-014, BR-014 | Automated | Commission increment (COM-20, engine 2.0) | Carried over
TC-F-015 | A group of 10 rooms is commissioned at a flat 8% | Verify a reservation holding 10 rooms uses the flat 8% group rate instead of the transient rates. | Direct booking holding 10 rooms. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: room.roomCount=10 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=10; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, effective rate 8% and commission USD 64.00 | High | Functional | functional, automation | COM-20, REQ-015, BR-015 | Automated | Commission increment (COM-20, engine 2.0) | New
TC-F-016 | 9 rooms keep the transient base rate | Verify the group rate does not apply below 10 rooms. | Direct booking holding 9 rooms. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: room.roomCount=9 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=BAR; room.roomCount=9; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, effective rate 10% and commission USD 80.00 | High | Functional | functional, automation | COM-20, REQ-015, BR-015 | Automated | Commission increment (COM-20, engine 2.0) | New
TC-F-017 | Package rates are commissioned on 70% of the package price | Verify a PKG reservation is commissioned at 10% of 70% of the package price. | Package booking priced USD 1000.00 (no tax, fees or ancillaries). | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: rate.planCategory=PKG, revenue.totalAmount=1000 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=PKG; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=0; revenue.resortFeeAmount=0; revenue.ancillaryAmount=0; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, basis USD 700.00 and commission USD 70.00 | High | Functional | functional, automation | COM-20, REQ-016, BR-016 | Automated | Commission increment (COM-20, engine 2.0) | New
TC-F-018 | Negotiated corporate rates are commissioned at a flat 5% | Verify a CORP rate-plan reservation is commissioned at 5% with no uplifts or bonuses. | Direct booking on a negotiated corporate rate plan. | 1. Build a full reservation from the SUT data dictionary (all attributes, dictionary example values) 2. Override the commission drivers: rate.planCategory=CORP 3. POST /api/commission/quote 4. Read the commission breakdown | reservation.status=CONFIRMED; channel.bookingChannel=DIRECT; stay.nights=3; rate.planCategory=CORP; room.roomCount=1; payment.loyaltyPointsRedemption=false; revenue.totalAmount=1000; revenue.taxAmount=120; revenue.resortFeeAmount=30; revenue.ancillaryAmount=50; every other attribute of the 1000-attribute reservation from the data dictionary examples | HTTP 200, effective rate 5% and commission USD 40.00 | High | Functional | functional, automation | README.md, src/rules.js, REQ-017, BR-017 | Automated | Commission increment (COM-20, engine 2.0) | New
Note on G10: Superseded (v1): HTTP 200, capped = true and commission USD 500.00

## Execution
Case | Requirement | Name | Result | Duration ms | Note
TC-F-001 | REQ-001 | The reservation model has 1000 attributes and a full reservation is accepted | passed | 27
TC-F-002 | REQ-002 | Advisor views the commission breakdown on the commission statement page | passed | 227
TC-N-001 | REQ-003 | Commission quote p95 response time is within 300 ms | passed | 51
TC-F-003 | REQ-004 | Base commission is 10% of commissionable room revenue | passed | 9
TC-F-004 | REQ-005 | Taxes, resort fees and ancillaries are excluded from commissionable revenue | passed | 6
TC-F-005 | REQ-006 | GDS reservations earn an additional 1.5% channel uplift | passed | 9
TC-F-006 | REQ-007 | A stay of exactly 7 nights earns the 1.5% long-stay bonus | failed | 6
TC-F-007 | REQ-007 | A stay of 6 nights earns no long-stay bonus | passed | 22
TC-F-008 | REQ-008 | Commission is capped at USD 750 per reservation | passed | 11
TC-F-009 | REQ-009 | Commission is rounded half-up to 2 decimal places | passed | 10
TC-F-010 | REQ-010 | A stay paid with loyalty points earns no commission | passed | 9
TC-F-011 | REQ-011 | Cancelled and no-show reservations earn no commission | passed | 9
TC-F-012 | REQ-012 | Verify: Every commission calculation is written to the commission audit ledger | not-run | 0 | Manual test case - not automated, not executed
TC-F-013 | REQ-013 | A reservation without an advisor IATA number returns HTTP 422 | passed | 11
TC-F-014 | REQ-014 | Commission for an unknown reservation ID returns HTTP 404 | passed | 3
TC-F-015 | REQ-015 | A group of 10 rooms is commissioned at a flat 8% | passed | 6
TC-F-016 | REQ-015 | 9 rooms keep the transient base rate | passed | 6
TC-F-017 | REQ-016 | Package rates are commissioned on 70% of the package price | passed | 6
TC-F-018 | REQ-017 | Negotiated corporate rates are commissioned at a flat 5% | passed | 5

## Defects
ID | Title | Severity | Case | Requirement | Expected | Actual | Failing assertion | Movement
DEF-001 | A stay of exactly 7 nights earns the 1.5% long-stay bonus: returns 80 instead of 92 | Critical | TC-F-006 | REQ-007 | 92 | 80 | expect(r.body.commission).toBe(92); | still open

## Coverage
Requirement | Text | Cases | Automated | Executed | Failed | Status
REQ-001 | Every reservation is described by a data dictionary of 1000 attributes. | 1 | 1 | 1 | 0 | executed - passing
REQ-002 | Travel advisors can view the commission breakdown for a reservation online. | 1 | 1 | 1 | 0 | executed - passing
REQ-003 | Commission quotes return within 300 ms at the 95th percentile. | 1 | 1 | 1 | 0 | executed - passing
REQ-004 | Base commission is 10% of commissionable room revenue. | 1 | 1 | 1 | 0 | executed - passing
REQ-005 | Commissionable room revenue excludes taxes, resort fees and ancillary charges. | 1 | 1 | 1 | 0 | executed - passing
REQ-006 | Reservations booked through the GDS channel earn an additional 1.5% channel uplift. | 1 | 1 | 1 | 0 | executed - passing
REQ-007 | Stays of 7 nights or more earn a long-stay bonus of 1.5%. | 2 | 2 | 2 | 1 | executed - failing
REQ-008 | Commission per reservation is capped at USD 750. | 1 | 1 | 1 | 0 | executed - passing
REQ-009 | Commission is rounded half-up to 2 decimal places. | 1 | 1 | 1 | 0 | executed - passing
REQ-010 | Reservations paid with loyalty points are not commissionable. | 1 | 1 | 1 | 0 | executed - passing
REQ-011 | Cancelled and no-show reservations earn no commission. | 1 | 1 | 1 | 0 | executed - passing
REQ-012 | Every commission calculation is written to the commission audit ledger. | 1 | 0 | 0 | 0 | designed only (manual)
REQ-013 | A reservation without an advisor IATA number returns HTTP 422. | 1 | 1 | 1 | 0 | executed - passing
REQ-014 | Unknown reservation IDs return HTTP 404. | 1 | 1 | 1 | 0 | executed - passing
REQ-015 | Group reservations of 10 or more rooms are commissioned at a flat 8%. | 2 | 2 | 2 | 0 | executed - passing
REQ-016 | Package rates are commissioned on 70% of the package price. | 1 | 1 | 1 | 0 | executed - passing
REQ-017 | Negotiated corporate rates (rate plan CORP) are commissioned at a flat 5%. | 1 | 1 | 1 | 0 | executed - passing

## Attribute coverage
Attribute | Description | Varied by cases | Status
reservation.status | Lifecycle status of the reservation | TC-F-011 | exercised - passing
stay.nights | Number of room nights | TC-F-006, TC-F-007 | exercised - failing
room.roomCount | Number of rooms held under the reservation | TC-F-015, TC-F-016 | exercised - passing
rate.planCategory | Category of the booked rate plan | TC-F-017, TC-F-018 | exercised - passing
revenue.totalAmount | Gross amount charged, including taxes, fees and ancillaries | TC-F-008, TC-F-009 | exercised - passing
revenue.taxAmount | Taxes included in revenue.totalAmount | TC-F-004 | exercised - passing
revenue.resortFeeAmount | Resort fees included in revenue.totalAmount | TC-F-004 | exercised - passing
revenue.ancillaryAmount | Ancillary charges (spa, dining, parking) included in revenue.totalAmount | TC-F-004 | exercised - passing
channel.bookingChannel | Channel the reservation was booked through | TC-F-005 | exercised - passing
advisor.iataNumber | IATA number of the booking travel advisor | TC-F-013 | exercised - passing
payment.loyaltyPointsRedemption | True when the stay is paid with loyalty points | TC-F-010 | exercised - passing

## Approvals
Gate | Decision | By | When | Detail
Requirement set review | approved | Priya Shah | 2026-10-02T04:13:58.150Z | 14 requirements approved; 0 excluded; 0 conflict(s) resolved
Merge into baseline | approved | Sam Lee | 2026-10-02T04:13:58.167Z | 4 requirements, 5 test cases, 4 scripts merged: BL-4 v1 -> v2

## Skills
Skill id | Name | Description | Seen by agents | File
automation-script-conventions | Automation script conventions | How every generated Playwright spec is shaped, named and asserted, so scripts stay reviewable and runnable cycle after cycle. | scripts | automation-script-conventions.md
cycle-report | Test cycle report | The fixed shape of every cycle report, so two cycles can be read side by side without translation. | report | cycle-report.md
defect-reporting | Defect reporting | What a defect must contain before it is raised, so every cycle's defects read the same and are actionable. | defects | defect-reporting.md
incremental-merge | Incremental load and merge rules | How an addition is classified against the baseline and what a human must see before it merges. | delta, rules, testcases, scripts | incremental-merge.md
input-normalisation | Input normalisation and provenance | How several inputs become one requirement set, and what must be visible about where each statement came from. | normalise, rules | input-normalisation.md
input-review | Input review before the human gate | What the review agent checks in the project inputs and how it words its suggestions for the reviewer. | review-agent | input-review.md
test-case-authoring | Test case authoring and Zephyr export shape | One house style for every test case, so each cycle exports into Zephyr the same way. | testcases, report | test-case-authoring.md
test-data-generation | Test data generation from the input specs | Every test case gets a complete, spec-conformant data set built from the data dictionary in the codebase input. | testdata | test-data-generation.md
testing-regression | Regression pack | Steers the design and execution agents to keep and re-run the full pack so nothing that worked before breaks. | testcases, scripts, execution | testing-regression.md
traceability-handover | Traceability hand-over | What each phase owes the next one so the chain from input to defect never breaks in any cycle. | normalise, requirements, rules, testcases, testdata, scripts, execution, defects, report | traceability-handover.md

## Hand-overs
Phase | Skills seen | Hand-over | Missing | Artefacts owed
Normalise (3-way compare) | input-normalisation, traceability-handover | complete |  | statements: delivered; gaps: delivered; conflicts: delivered
| input-review | complete |  | suggestions: delivered
Delta classification | incremental-merge | complete |  | delta: delivered
Requirements repository agent | traceability-handover | complete |  | requirements: delivered
Business rules agent | incremental-merge, input-normalisation, traceability-handover | complete |  | businessRules: delivered
Test case agent | incremental-merge, test-case-authoring, testing-regression, traceability-handover | complete |  | functional: delivered; nonFunctional: delivered; regressionPack: delivered
Test data agent | test-data-generation, traceability-handover | complete |  | dataSets: delivered; specConformance: delivered
Automation script agent | automation-script-conventions, incremental-merge, testing-regression, traceability-handover | complete |  | specs: delivered
Execution agent (Playwright, real run) | testing-regression, traceability-handover | complete |  | results: delivered
Defect agent | defect-reporting, traceability-handover | complete |  | defects: delivered
Cycle report agent | cycle-report, test-case-authoring, traceability-handover | complete |  | cycleReport: delivered; comparison: delivered; testCaseExport: delivered